## Projekt 1
Att göra-lista
Ansvarig : |  | Peter Karlsson
Start datum: |  | 09-02-2026
Projekt 1
% klart | Uppgift | Utfört | Utfört av
100% | Clean the fans in all houses | 10-02-2026 | Florence & Aphrodis
100% | Remove everything that you dont use | 10-02-2026 | Florence & Aphrodis
100% | Fix water hose in house 15 | 11-02-2026 | Aurimas & Jonas
100% | Throw fridges in house 11 | 13-02-2026 | Nenad & Miroslav
100% | Fix egg-wire in house 14 | 17-02-2026 | Florence & Aphrodis
100% | Fix light in house 14 & 15 | 17-02-2026 | Florence & Aphrodis
100% | Change side on wires on winch in house 13 | 24-02-2026 | Aurimas & Jonas
100% | Doors on backside in 13 & 15 | 24-02-2026 | Aurimas & Jonas
100% | Gap on door on front-side in house 13 | 24-02-2026 | Aurimas
100% | Clean in the hallways in all stables | 17-02-2026 | Florence & Aphrodis
100% | Fix net on gate in house 11 | 13-02-2026 | Rizwan
100% | Oil the shitband chain on all houses | 10-02-2026 | Florence & Aphrodis
0% | Clean the white belt on all houses
20% | Clean the rooms with the compressor in stables.
100% | Fix the roof for water in house 14. Spare parts in garage. | 13-02-2026 | Florence & Aphrodis & Aurimas
100% | Fix nets around the ventelation in the cealing | 13-03-2026 | Nenad
100% | Clean the garage | 07-04-2026 | Peter & Johan
50% | Dig in stable 11 | March - | Everybody
50% | Dig in stable 12 | March - | Everybody
50% | Dig in stable 13 | March - | Everybody
50% | Dig in stable 14 | March - | Everybody
50% | Dig in stable 15 | March - | Everybody